Tractor Pull Contestant Registration

Chairman’s Planning Guide

PLANNING

1.	PRIMARY PURPOSE

The primary purpose of this project is to raise funds to help pay for the Tractor Pull.

2.	GIVE A BRIEF DESCRIPTION OF THE PROPOSED PROJECT AND BACKGROUND INFORMATION. FOLLOW THIS WITH A LISTING OF THE SPECIFIC AND MEASURABLE GOALS TO BE ACCOMPLISHED BY THIS PROJECT.

DESCRIPTION

The Auburn  Jaycees plans to run a successful Tractor Pull in 2007.  To do this following the Nebraska Power Pullers truck show we have a Farm Tractor Show. For the Farm Tractor Show we charge contestants $20.00 a pull. We offer 14 different weight classes. To run this project we need to run a registration table where we will have all contestants sign in. We will need to have two persons to keep score in each of the classes, one person to write checks to the winners, and one person to announce. This is a great opportunity for the Auburn Jaycees to make money for the chapter and to learn how to work as a team. This project relates to our Chapter Plan in the Business area in the Financial Management commission.

GOAL 1: To raise $500 to help with the Tractor Pull expenses.

GOAL 2: To have 100 pulls in the Farm Pull.

GOAL 3: To involve four members in the project.

3. LIST THE SPECIFIC MANPOWER ASSIGNMENTS

Project Chairperson/Treasurer

Tina Kahanca

73103 640th Ave.

Auburn, NE 68305

(402) 274-7765

Duties/Responsibilities As Chairperson:.

	Promote the project at GMMs.

	Make sure there are plenty of blank checks for payouts. It will take at least one box of checks. Better have

two boxes of checks just to be safe.

	Put together a contestant registration form for each of the entrants.

	Have each entrant under 18 have a parent sign a waiver form.

	Make plenty of copies of the payback form

	Have pull tabs for each of the Tractor classes.

	Have a driver and weight class sheet for each driver to put on the side of their tractor.

	Line up an announcer to help at the contestant registration table.

	Write the CPG.

Duties/Responsibilities As Treasurer:

	Monitor financial status of the project.

	Assist in adhering to an approved budget.

	Provide funding for the project as funds are requested, subject to receipts being turned in.

Chapter President

Susan Stough

1202 24th St.

Auburn, NE 68305

(402) 274-1432

Duties/Responsibilities:

	Oversees the chapter and all projects run.

Supervising Vice President

Eldon Russell

128 Park Ave.

Humboldt, NE 68376

(402) 862-3283 (h) or (402) 862-5269 (c)

Duties/Responsibilities:

	 Oversee the project to ensure it meets the goals of the area and the goals of the chapter.

Secretary

Angela Wredt

1020 O St.

Auburn, NE 68305

(402) 274-7625

Duties/Responsibilities As Secretary:

	Keep records of correspondence pertaining to this project.

	Maintain needed supplies for this effort.

	Record all proceedings relating to this project at meetings.

Chapter Members:

	Attend monthly general membership meetings to keep informed of the project.

4.  LIST SPECIFIC MATERIALS, SUPPLIES AND RESOURCES REQUIRED:

Material/Supply	Member Assigned	Vendor/Supplier	Date Needed		Donation/Purchase/

Own       __

Newsletter		Susan Stough		Chapter Supply	4/1, 5/1, 6/1, 7/1	Own

CPG Materials		Eldon Russell		Pamida			4/1			Purchase

2 Reams of Paper	Tina Kahanca		Pamida			7/7			Purchase

2 boxes of checks	Tina Kahanca		Carson National Bank	7/8			Purchase

Names and Addresses:

Name & Address: Pamida, 2410 Dahlke Ave., Auburn, NE 68305

What: Ream of Paper, CPG Supplies

Name & Address:  Carson National Bank, 2301 Dahlke Ave., Auburn, NE

Phone: (402 ) 274-4333

What:  Start Up Cash

5. DESCRIBE POTENTIAL PROBLEMS AND THEIR SOLUTIONS TO SUCCESSFULLY COMPLETE THIS PROJECT:

Problem: Not able to keep up with all the registrations.

Solution: Have at least three people helping to register contestants.

Solution: Start registration at 2:30 and run until 6:30 so it’s spaced out a bit.

Problem: Not having enough forms.

Solution: Print 100 sheets of each form. If we have extras we’ll save them for next year.

6.  COMPLETE A PROPOSED BUDGET SHOWING ALL ANTICIPATED INCOME AND EXPENSES:

INCOME:					PROPOSED				ACTUAL

(Value of Donated Items)

Newsletter					5.00

Pen (1)						1.00

Sign In Sheet					  .20

Computer				        800.00

Printer					          50.00

Ink Cartridge				          30.00

Total Donated Items			     $886.20

Registration  Income 			      2000.00

TOTAL INCOME			     $2886.20

EXPENSES:

Value of Donated Items		          886.20

CPG Materials					  5.00

2 Reams of Paper				12.00

2 boxes of checks				15.00

Payouts				        1500.00

Return to the Chapter			         468.00

TOTAL EXPENSES			      $2886.20

7. LIST THE SPECIFIC STEPS TO BRING THIS PROJECT TO A SUCCESSFUL COMPLETION SHOWING PLANNED DATES FOR EACH STEP.

1/15/06-	Project approved at Board Meeting.

2/3/06-	Promote project at GMM.

4/1/06-	Start CPG process.

4/4/06-	Promote project at GMM.

5/2/06-	Make update of project at GMM.

5/15/06-	Order 2 books of checks for the Pull.

5/25/06-	Create waiver forms, registration forms, pull tabs, and payback form. Use Humboldt’s forms

as a sample to create ours.

6/1/06-	Ask Humboldt Jaycees to use some of their score sheets.

6/6/06-	Make report at GMM.

6/15/06-	Purchase 2 reams of paper.

6/20/06-	Ask Eldon to make copies of all forms, payout sheets, pull tabs, registration forms, and driver

and weight class form.

7/8/06-	Day of the event. Make sure all forms are organized and you are ready to start signing up

contestants starting at 2:30 p.m. You will sign up contestants until 6:30 p.m. The Farm Pull

itself will start at approximately 10:30 p.m.

7/12/06-	Following the Pull send a thank you note to everyone that helped at the contestant table.

7/18/06-	Make report at GMM.

8/15/06-	Make final report at GMM.

9/1/06-	Complete CPG.

IMPLEMENTATION AND EVALUATION

8. RECORD ANY REVISION OF THE ORIGINAL PLAN.

6/15/06-  Asked Finch to help out with announcing since we were borrowing his sound system

for the Pull.

6/15/06-  We also asked Lisa Gebers to help with the contestant table to help check in contestants

and to help with keeping score.

9. WHAT CHANGES OR RECOMMENDATIONS DO YOU HAVE FOR A FUTURE CHAIRPERSON?

It is suggested to have printed rule sheets for all contestants. Fewer questions that way.

Have David put together an exact order of how the Pull will be run so that the contestant table knows

a little more.

Need startup cash.  We didn’t have start up cash this year- we figured most pullers would pay by check.

10. GIVE SPECIFIC AND MEASURABLE GOALS FOR EACH GOAL ESTABLISHED. DESCRIBE THE IMPACT OF THIS PROJECT ON THE CHAPTER, INDIVIDUAL MEMBERS AND THE COMMUNITY. EVALUATE THE PRIMARY PURPOSE.

Primary Purpose:  The primary purpose of this project is to raise funds to help pay for the Tractor Pull.

Result:   We made $507.45 after all expenses were paid from the contestant table.   It’s impossible to

lose money in a farm pull. We give back 75% of what is collected in each class.

GOAL 1: To raise $500 to help with the Tractor Pull expenses.

RESULT: The profit was $507.45 after payouts.

GOAL 2: To have 100 pulls in the Farm Pull.

RESULT: We had 115 pulls.

GOAL 3: To involve four members in the project.

RESULT: The following people worked at the contestant table: Tina, John, Rob Reed, Lisa Gebers and our announcer Brian Finch.

PROJECT IMPACT:

ON THE CHAPTER:

The impact this project had on the chapter was that it helped increase the community awareness of the organization. This helps attract new members throughout the community.

We provided the community with the idea that the Jaycees are a strong, established organization that works together.

ON THE INDIVIDUAL:

This project motivated members to help raise money for the chapter.

The individual members that were involved with this project were able to see how creating a plan of action and following it you can run a successful project.

The individual was able to improve their management skills by working this project.

ON THE COMMUNITY:

The community benefited by having information provided to them about the Jaycees.

The community sees how the Jaycees work together and the amount of work it takes to put together a project of this magnitude.

The community of Auburn benefits by the donations made by the Jaycees on an annual basis.

The money raised will be returned to the community with various community service projects that we help sponsor.

INCOME:				   PROPOSED			     ACTUAL

(Value of Donated Items)

Newsletter					5.00					5.00

Pen (1)						1.00					1.00

Sign In Sheet					  .20					  .20

Computer 				         800.00				         800.00

Printer				                       50.00				           50.00

Ink Cartridge				           30.00				           30.00

Total Donated Items			      $886.20				       $886.20

Registration Income			      2000.00				       2400.00

TOTAL INCOME			     $2886.20		                             $3286.20

EXPENSES:

Value of Donated Items		          886.20				          886.20

CPG Materials					  5.00					  6.25

2 Reams of Paper				12.00					11.00

2 boxes of checks				15.00					15.00

Payouts				         1500.00				        1860.00

Return to the Chapter			            273.00				          507.45

TOTAL EXPENSES			       $2886.20				       $3286.20