Fair Bingo

Chairman’s Planning Guide

PLANNING

1.	PRIMARY PURPOSE

The primary purpose of this project is to raise funds for the chapter’s general fund.

2.	GIVE A BRIEF DESCRIPTION OF THE PROPOSED PROJECT AND BACKGROUND INFORMATION. FOLLOW THIS WITH A LISTING OF THE SPECIFIC AND MEASURABLE GOALS TO BE ACCOMPLISHED BY THIS PROJECT.

DESCRIPTION

The Auburn  Jaycees runs a bingo stand every year during the Nemaha County Fair as a chapter fundraiser. The stand is open for three nights and runs for three hours each evening. This project is a tradition in the community and a project that everyone looks forward to attending each year at the county fair. We will need to reserve a spot on the fairgrounds, apply for a special event Bingo license, set up our tent, reserve picnic tables with the city, and line up plenty of manpower for the three nights of Bingo. This is a great opportunity for the Auburn Jaycees to make money for the chapter and to learn how to work as a team. This project relates to our Chapter Plan in the Business area in the Financial Management commission.

GOAL 1: To run a project that raises $900.00 for the chapter’s general fund.

GOAL 2: To involve at least seven members in a project.

GOAL 3: To activate two members.

GOAL 4: To involve five Jaycees from other chapters.

3. LIST THE SPECIFIC MANPOWER ASSIGNMENTS

Project Chairperson/Supervising Vice President

Eldon Russell

128 Park Ave.

Humboldt, NE 68376

(402) 862-3283 (h) or (402) 862-5269 (c)

Duties/Responsibilities As Co- Chairperson:

 	Present project at board meeting for approval.

	Secure manpower to work the stand. We need a total of 5 people per shift.

	Promote the project at GMMs.

	Contact the city and request that we use the city park picnic tables for the event.

	Prepare a sign-up sheet to hand out at meetings to sign up members to work.

	Secure a tent for the stand.

	Write newsletter article about the project.

	Attend the project and work the stand.

	Reserve Fair Booth Space.

	Write the CPG.

Duties/Responsibilities as Vice President:

	Oversee the project to ensure it meets the goals of the area and the

goals of the chapter.

Chapter President/Co-Chairperson

Susan Stough

1202 24th St.

Auburn, NE 68305

(402) 274-1432

Duties/Responsibilities As Co- Chairperson:

	Help secure manpower to work the stand. We need a total of 5 people per shift..

	Promote the project at GMMs.

	Take care of the bingo supplies such as cards, bingo machine, P.A. system, etc.

	Attend the project and work the stand.

	Write the CPG.

Duties/Responsibilities As President:

	Oversees the chapter and all projects run.

Secretary

Angela Wredt

1020 O St.

Auburn, NE 68305

(402) 274-7625

Duties/Responsibilities As Secretary:

	Keep records of correspondence pertaining to this project.

	Maintain needed supplies for this effort.

	Record all proceedings relating to this project at meetings.

Treasurer/Committee Member

Tina Kahanca

73103 640th Ave.

Auburn, NE 68305

(402) 274-7765

Duties/Responsibilities As Committee Member:

	Apply for the Bingo license.

	Contact the city about installing a powerbox for the event.

	Get the startup cash for the event.

Duties/Responsibilities As Treasurer:

	Monitor financial status of the project.

	Assist in adhering to an approved budget.

	Provide funding for the project as funds are requested, subject to receipts being turned in.

Chapter Members:

	Attend monthly general membership meetings to keep informed of the project.

	Attend the project and work the stand.

4.  LIST SPECIFIC MATERIALS, SUPPLIES AND RESOURCES REQUIRED:

Material/Supply	Member Assigned	Vendor/Supplier	Date Needed		Donation/Purchase/

Own       __

Newsletter		Susan Stough		Chapter Supply	6/1, 7/1, 8/1		Own

CPG Materials		Eldon Russell		Pamida			6/1			Purchase

Tent			Rhonda Mueller	Chapter Supply	8/6			Donation

Picnic Tables		Rhonda Mueller	City of Auburn	8/6			Donation

PA System		Susan Stough		Chapter Supply	8/7			Donation

Electric Powerbox	Tina Kahanca		Board of Public Works 8/7			Purchase

Bingo Cards		Susan Stough		Chapter Supply	8/7			Donation

Bingo Machine	Susan Stough		Chapter Supply	8/7			Donation

Fliers			Eldon Russell		Chapter Supply	7/20			Donation

Member Roster	Eldon Russell		Chapter Supply	7/20			Donation

Mem. Brochures	Eldon Russell		Chapter Supply	8/7			Own

Money Aprons (3)	Tina Kahanca		Chapter Supply	8/7			Own

$200 start up cash	Tina Kahanca		Carson National Bank	8/7			Purchase

Names and Addresses:

Name & Address: Pamida, 2410 Dahlke Ave., Auburn, NE

What: Ream of Paper, CPG Supplies

Name & Address: City of Auburn,  1101 J St., Auburn, NE

Phone: (402) 274-3420

What: picnic tables

Name & Address: Board of Public Works

Phone: (402 ) 274-4981

What:  power box

Name & Address: Nebraska Department of Revenue, PO Box 94855, Lincoln, NE 68509-4855

What:  Bingo license

Name & Address:  Carson National Bank, 2301 Dahlke Ave., Auburn, NE

Phone: (402 ) 274-4333

What:  Start Up Cash

Name & Address:  Nemaha County Fair Board

Phone: (402 ) 274-4639

What:  Fair Booth

5. DESCRIBE POTENTIAL PROBLEMS AND THEIR SOLUTIONS TO SUCCESSFULLY COMPLETE THIS PROJECT:

Problem: Poor attendance of Jaycees to work.

Solution: Provide a copy of the signup sheet in the chapter newsletter.

Solution: Pass the signup sheet out during GMM’s.

Solution: Contact members by phone or e-mail a couple of weeks before the project to ensure enough manpower will be present.

Solution: Mail a flier promoting the project.

Solution: Contact other chapters and state board members to help work.

Problem: Not being able to open on time.

Solution: Have plenty of manpower between 6:30-7:00 to help setup`.

Solution: Be early in case of a problem with bingo machine or P.A. system.

Problem: Bad weather.

Solution: Bingo is played under a tent, so unless it’s dangerous lightning we’ll be good to go.

Solution: Bring the sides to the tents, will help keep the water out.

6.  COMPLETE A PROPOSED BUDGET SHOWING ALL ANTICIPATED INCOME AND EXPENSES:

INCOME:					PROPOSED				ACTUAL

(Value of Donated Items)

Newsletter					5.00

Pen (1)						1.00

Sign In Sheet					  .20

Brochures (100)			          20.00

Money Aprons (3)			          30.00

Tent					        175.00

Picnic Tables (16)			      1600.00

PA System				      1000.00

Electric Powerbox		                  5000.00

Bingocards				        100.00

Bingo Machine			        500.00

Computer				        800.00

Printer					          50.00

Ink Cartridge				          30.00

Camera & Film Developing		          15.00

Membership Roster			            1.00

Total Donated Items			     $9327.20

Bingo Sales			                   1000.00

TOTAL INCOME			     $10327.20

EXPENSES:

Value of Donated Items		        9327.20

Bingo License					25.00

Fair Booth Fee				            25.00

CPG Materials					  5.00

Startup Cash				          200.00

Return to the Chapter			           745.00

TOTAL EXPENSES			       $10327.20

7. LIST THE SPECIFIC STEPS TO BRING THIS PROJECT TO A SUCCESSFUL COMPLETION SHOWING PLANNED DATES FOR EACH STEP.

5/8/06-	Project approved at Board Meeting

5/17/06-	Promote project at GMM.

6/1/06-	Start CPG process.

6/6/06-	Promote project at GMM.

6/15/06-	Apply for bingo license.

6/15/06-	Reserve picnic tables with the city.

6/15/06-	Reserve one of our tents for that weekend.

6/15/06-	Reserve a spot with the Fair Board.

7/18/06-	Make update of project at GMM. Pass around sign-up sheet to work a shift.

7/25/06-	Contact the Board of Public Works to install a powerbox after the tent is up

7/25/06- 	Make phone calls and line up manpower. Also mail fliers to all members, other chapters,

and state board members about the project.

7/25/06-	Send e-mail to everyone on e-mail list. Also submit info on the project to the Jaycee E-news.

8/1/06-	Promote project at GMM.

8/2/06-	Go to the storage unit and make sure p.a. system and bingo supplies are all there

prior to the event. The payout sheets should be with the bingo cards.

8/5/06-	Send out reminder e-mail about the project.

8/6/06-	Set up the tent and go to the park and get the picnic tables.

8/6/06-	Make change order with bank.

8/7/06-	Confirm with the Board of Public Works in the morning that the power box is installed and

ready to go.

8/7/06-	Make sure you are there at 6:30 to set everything up.  You will need to have the

bingo cards on the table, bingo machine in place ready to start at 7 p.m. and set up

the p.a. system. Also make sure a sign-in-sheet is ready.

8/8/06-	Same procedure with setting up.

8/9/06-	Same procedure with setting up.

8/10/06-	Tear down the tent and take the picnic tables back to the park.

8/15/06-	Make final report at GMM.

9/1/06-	Finish CPG.

IMPLEMENTATION AND EVALUATION

8. RECORD ANY REVISION OF THE ORIGINAL PLAN.

7/25/06-   It was decided to post the information on the Got Jaycees Forums.

8/8/06-	    Our bingo equipment wasn’t running right so we borrowed bingo equipment from

Good Samaritan senior citizen home.

8/8/06-    Called more members to help out.  The first night there was not enough help.

8/8/06-    Called other chapters and state board members to help.

8/9/06-    Asked Finch to stay after the Parade to help in the bingostand.

9. WHAT CHANGES OR RECOMMENDATIONS DO YOU HAVE FOR A FUTURE CHAIRPERSON?

I would suggest that the chapter purchase a new bingomachine from Ebay or else watch the classified

Ads. Our equipment isn’t the best anymore.

We need to line up more manpower.  A few of us had to work all three nights for the entire 3 hour shift.

10. GIVE SPECIFIC AND MEASURABLE GOALS FOR EACH GOAL ESTABLISHED. DESCRIBE THE IMPACT OF THIS PROJECT ON THE CHAPTER, INDIVIDUAL MEMBERS AND THE COMMUNITY. EVALUATE THE PRIMARY PURPOSE.

Primary Purpose: The primary purpose of this project is to raise funds for the chapter’s general fund.

Result:  The chapter profited over $1,000 from this event which can now be used on other projects in our

community.

GOAL 1: To run a project that raises $900.00 for the chapter’s general fund.

RESULT: The profit from this project was $1,010.00.

GOAL 2: To involve at least seven members in a project.

RESULT: There were a total of nine members that helped with this event.

GOAL 3: To activate two members.

RESULT: Joe and Michelle Dixon were activated during this event.

GOAL 4: To involve five Jaycees from other chapters.

RESULT: We had nine Jaycees from other chapters help over the course of the three nights.

PROJECT IMPACT:

ON THE CHAPTER:

The impact this project had on the chapter was that it helped increase the community awareness of the organization. This helps attract new members throughout the community.

The members were able to get to know each other better while we were working at this project.

We provided the community with the idea that the Jaycees are a strong, established organization that works together.

The chapter can now use the money raised for more community projects.

ON THE INDIVIDUAL:

This project motivated members to help raise money for the chapter.

The individual members that were involved with this project were able to see how creating a plan of action and following it you can run a successful project.

The individual was able to improve their management skills by working a shift in the stand.

ON THE COMMUNITY:

The community benefited by having information provided to them about the Jaycees.

The community sees how the Jaycees work together and the amount of work it takes to put together a project of this magnitude.

The community learned that the Jaycees care about our community and want to raise money to help with community service projects.

The community of Auburn benefits by the donations made by the Jaycees on an annual basis.

The money raised will be returned to the community with various community service projects that we help sponsor.

INCOME:				   PROPOSED			     ACTUAL

(Value of Donated Items)

Newsletter					5.00					5.00

Pen (1)						1.00					1.00

Sign In Sheet					  .20					  .20

Brochures (100)			          20.00				          20.00

Money Aprons (3)			           30.00				          30.00

Tent					         175.00				         175.00

Picnic Tables (16)			        1600.00	                                           1600.00

PA System			     	        1000.00				       1000.00

Electric Powerbox			        5000.00				       5000.00

Bingocards				          100.00				         100.00

Bingo Machine			          500.00				         500.00

Computer				          800.00				         800.00

Printer				                       50.00				            50.00

Ink Cartridge				           30.00				            30.00

Camera & Film Developing		           15.00				            15.00

Membership Roster		            	 1.00					  1.00

Total Donated Items			     $9327.20				      $9327.20

Bingo Sales			  	     1000.00				       1267.09

TOTAL INCOME			     $10327.20		                            $10594.29

EXPENSES:

Value of Donated Items		        9327.20				        9327.20

Bingo License					25.00					25.00

Fair Booth Fee					25.00					25.00

CPG Materials					  5.00					  6.25

Startup Cash				          200.00				          200.00

Return to the Chapter			          545.00				        1010.84

TOTAL EXPENSES			       $10327.20		                $10594.29